## CHC Deferred Maintenance 2017
Crafton Hills College 5 Year Defered Maintenance 2019 - 2024
Asset ID | Description | Special Considerations | Identified In ISES Report | Projected Cost | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 2023/24
BL 1 M&O
| Replace existing galv domsetic water piping & BFD | Potential of interuptions of campus operations | Yes BL 1 pg 1.2.4 | 10000 | X
| Replace siding on existing storge facilitiy | Past expected life cycle | No | 25000 | X
BL 2 CDC
| Replace package HVAC units (5) | Potential unplanned interuption of CDC program and community services | YES BL 2 pg 2.3.2 | 95000 |  |  | X
| Interior Floors & Finishes | Past expected life cycle | YES BL 2 pg 2.1.1 | 165000 |  |  | X
| Replace existing HVAC controls | Past expected life cycle | YES BL 2 pg 2.3.2 | 20000 |  |  | X
| Replace Roof #1 & 2 | Past expected life cycle | YES BL 2 pg 2.3.2 | 45000 |  |  | X
| Replace exterior Siding on #3 | Past expected life cycle | YES BL 2 pg 2.3.2 | 12000 |  |  | X
| Install Interior lighting control system/Upgrade to LED | Past expected life cycle. Capture potential energy savings and incentives | YES BL 2 pg 2.3.2 | 90000 |  |  | X
| Repalce corrugated roof on #3 | Attained effective life cycle | YES BL 2 pg 2.3.3 | 20000 |  |  | X
| Replace BFD and water heaters | Past expected life cycle | YES BL 2 pg 2.3.2 | 10000 |  |  | X
| Installnew battery back up exit signage | Comply with current regulations | YES BL 2 pg 2.3.2 | 4500 |  |  | X
BL 3 CH | Special Note - This asset has been identified for reprogramming and complete renovation in the CHC Facilities Master Plan 2016. All asset systems and components have been identified as past expected life cycle per ISES Facilitiy Condition Report 2016. | All improvements recommended are to allow for some occupancy until complete renovation and funding is in place. Expectation is for 3-5years until renovation.
| Roof Replacement | Past expected life cycle | YES BL 3 pg 2.3.2 | 45500 |  |  |  | X
| Flooring replacement | Past expected life cycle | YES BL 3 pg 2.3.2 | 30000 |  |  |  | X
| Repair of existing domestic water supply in service area | Past expected life cycle. System failure is imminent. | YES BL 3 pg 2.3.2 | 45000 |  |  |  | X
| Replacement of Air Handler | Past expected life cycle. System failure is imminent. | YES BL 3 pg 2.3.2 | 350000 |  |  |  | X
BL 4 CTB
Complete renovation 2017. No recommendations for improvements .
BL 5 WEST
| HVAC AH Replacement | Past expected life cycle | YES BL 5 pg 2.3.2 | 50000 |  |  | X
| ADA Compliance upgrade | Needed for compliance | YES BL 5 pg 2.3.2 | 8000 |  |  | X
| Fire System Upgrade | Needed for compliance. Building does not have interior sprinklers | YES BL 5 pg 2.3.2 | 200000 |  |  | X
BL 6 CCR | New asset in 2015. No items identified for improvements within 5 years.
BL 7 SSB
| Elevator Upgrade | Bring elevator up to current standards | YES BL 7 pg 2.3.2 | 61000 |  |  |  | X
| Replace HVAC controls | Past expected life cycle | YES BL 7 pg 2.3.2 | 28000 |  |  |  | X
| Seal Exterior CMU Walls | Past expected life cycle | Yes BL 7 pg 2.4. 1 | 10500 |  |  |  | X
| Install new Exit signage w/batttery back up. | Improved occupant safety | YES BL 7 pg 2.3.2 | 5000 |  |  |  | X
| Replace RR exhaust fans | Past expected life cycle | YES BL 7 pg 2.3.2 | 8500 |  |  |  | X
BL 8 LRC | Asset constructed in 2010. Minor upgrades noted
| Replace BFD's | Past expected life cycle | Yes BL 8 pg 2.3.2 | 23000 |  | X
| Replace existing FCI Fire Panel and devices | Conform to campus standards | No | 200000 |  | X
BL 9 PAC | Special Note - This asset has been identified for reprogramming and complete renovation in the CHC Facilities Master Plan 2016. All asset systems and components have been identified as past expected life cycle per ISES Facilitiy Condition Report 2016. | Minor reovations to some program areas, elvators, sewage ejector , and egress lighting were executed in summer 2017. No further immediate needs have been defined.
BL 10 CNTL 1 | Complete renovation 2017 of occupied areas. No recommendations for improvements. Central Plant hosed in BL 10 was not included in 2017 renovation.
| Cooling Tower Replacement | Cooling towers will reach expected life cycle in 2021. Interior refurbishmet done in 2014. This allowed for equipment life to extend to 20 year life cyce. Complete replcement should be considered for 2021/22 | No. FCI report did not include Central Plant Equipment | 300000 |  |  |  |  | X
| Central Plant HVAC equipment control upgrade | Central plant controls are close to expected life cyle due to obsolence of electronic hardware and soft ware. Existing EMS control system in has not been migrated inot the campus standard ALERTON EMS contorols system. | No. FCI report did not include Central Plant Equipment | 300000 |  |  |  |  | X
BL 11 CNTL 2 | Assset system noted for significant renovations in ISES Facility Condition Report 2016 | Improvements noted below are to allow for continued programatic use and occupancy until funding for complete facilility renovation is secured.
| Elevator Upgrade | Bring elevator up to current standards | YES BL 11 pg 2.3.2 | 240000 | X
| HVAC AHU, VFD, replacement | Past expected life cycle | YES BL 11 pg 2.3.2 | 142000 | X
| Interior lighting control sytem and LED upgrade | Past expected life cycle. Capture potential energy savings and incentives | YES BL 11 pg 2.3.2 | 81500 | X
| Replace HVAC controls | Existing controls obsolete. Migragte asset to Alerton EMS. | YES BL 11 pg 2.3.2 | 103000 | X
| Upgrade Lecture halls finishes, floors, stadium seating | Past expected life cycle | YES BL 11 pg 2.3.2 | 75000 | X
BL 12 CYN | New asset in 2015. No items identified for improvements within 5 years
BL 13 ARTS | Special Note - This asset has been identified for replacement in the CHC MP 2016. Any improvemnts need to be considered within this context. Funding for replacement has not been identified. Asset to remain viable and active for of 10 -12 years. All exixting systems /equipment are past expected life cycle. and must be replced to maintain viability of asset. years. | Interior renovations were executed within the south 1/2 in 2016. North 1/2 interiors to be upgraded in 2017.
| HVAC AHU renovation or replacement | Past expected life cycle. Equipment critical to program and occupancy. | YES BL 13 pg 2.3.2 | 200000 |  | X
| Art Lab flooring replacement | Past expected life cycle | YES BL 13 pg 2.3.2 | 32000 |  | X
BL 14 EAST 1 | Complete renovation executed in summer of 2019. | Non needs withn 5 years of 2019.
BL 15 EAST 2 | Special Note - This asset has been identified for replacement in the CHC MP 2016. Any improvemnts need to be considered within this context. Funding for replacement has not been identified. Asset to remain viable and active for a mininum of 10 years. | Interior classrooms and offices renovated in 2016. Roof restoration in 2016, life expectancy 5 years.
| Roof Replacement | Roof past expected life cycle. | No. BL 15 was not include in ISES inspection due to below 5000 sq. ft minimum threshold. | 60000 |  | X
| HVAC Equipment Refurbish | HVAC past expected life cycle | No. BL 15 was not include in ISES inspection due to below 5000 sq. ft minimum threshold. | 12000 | X
BL 16 PSAH | New asset in 2015. No items identified for improvements within 5 years
BL 17 GYM | Special Note - This asset has been identified to be removed by the CHC MP2016 and the 2016 ISES report. Asset not occupied or viable for occupancy | Demo of GYM is scheduled for 2020
| Demo of building | Past expected life cycle. | Yes BL 17 pg 1.1.1 | 750000 |  | X
BL 18 NRTH | Asset constructed in 2012. Minor upgrades noted in ISES Facility Condition Report 2016. No improvements identified within 5 years.
BL 19 KHA
| Replace BFD's | Past expected life cycle. | Yes BL 19 pg 2.3.2 | 14000 |  |  |  | X
| Security System Upgrade | Increase occupant and asset safety. Reduce campus liabilities. | No | 25000 | X
Site Infrastructure
| Replace Campus Extrior Lighting Control System | Exisisting EXERGY exterior control system is not supported and obsolete. Mission critical system for occupant safety and night operations. | No | 400000 | X
| Resurface all campus parking lots. | Existing parking lot surfces are past life cycle and in need or resurfacing. Additional risks imposed on occupants and District for potential trip hazards. Some Parking lot s will be resurfaced with renovation/consturtion projects | No | $250000 annually for next 5 years | X | X | X | X | X
| Replace existing Irrigation contorl system. | Exisitng irrigation controllers and control system are obsolete and past expected life cycle. A modern irrigation cotrol system will enhance ability of campus to meet State requirements for water use reductions. | No | 300000 |  | X
| Campus Security Upgrades | Install security survelience and access control systems across campus. Increased security bennifits to occupants and risk mitigation to SBCCD. | No | $220,000 annually for next 5 years. | X | X | X | X | X
Annual Total |  |  |  |  | 1773500 | 2035000 | 1189500 | 2557000 | 1070000